Proposal for the West Australian Project

Title

The Sheep at School

Objectives

- To increase the knowledge and understanding by teachers of the high level of science underpinning the Australian wool industry.

- To increase the knowledge and understanding by teachers of the links between the sheep wool and meat industry, research and education.

Scope

A half day professional learning and curriculum development session for 8 secondary teachers will enhance their knowledge and understanding of the value of the sheep industry to a range of education subjects beyond science. This will include industry and research speakers to teachers and later to students which will promote the broad range of careers available in agriculture and the wool industry in particular.

Mid June will see the sheep come to school.

Here, 500 hundred secondary students at Shenton College, Western Australia, will be greeted on arrival to school with a flock of sheep being ‘worked’ by a sheep dog on their school oval. Various sheep related activities will be engaged in throughout the day. These activities will promote the sheep industry as part of our scientific, economic and social culture.

Reason

The recently released Creating our Future Report1   (p106-109) highlights that Australian ‘farm and food business is becoming increasingly sophisticated, requiring a increasingly sophisticated and skilled workforce. ‘The number of university graduates involved in agriculture has tripled in 20 years to 2004, however, recent years has shown a decline in interest in agriculture at higher education institutions.’ Lastly, this report states that ‘it is important that the proportion of workers in agriculture with post-school qualifications grows over time with…a long term decline in the number of university graduates in agriculture could adversely affect the sector’s ability to change and adopt new practices.’

Outputs

- Professional learning, teaching and learning program development and networking session between teachers, a University of Western Australia researcher, Department of Agriculture (WA) agent and a wool  industry representative .

- Promoting rural science in an urban community.

- A model for similar sessions across other agricultural sectors.

- A project proposal to build sustainable rural communities by supporting, developing and promoting Western Australia’s agricultural sector careers and opportunities.

Measuring The Success Of The Initiative

- Successful delivery of the professional learning and program development session.

- The active participation of teachers and students in the ‘Sheep at School’ day

- The production and presentation of student work post participation in the day.

- Analysis of pre and post session survey.

Resources

UWA:

Dr Ian Williams, Faculty of Natural and Agricultural Sciences

Colin Hawke, Faculty of Natural and Agricultural Sciences

Dept. of Agriculture:

Katrina Bonser, Community Liaison Officer

Shenton College:

Staff

Primary Industry:

Peter Dowdall, White Suffolk Stud, Kojonup.

Suffolk Stud, Lake Grace

Primaries of W.A. Pty Ltd

| Key Stakeholders Australian Wool CRC Department of Agriculture, Government of Western Australia University of Western Australia University of Tasmania Department of Education, Western Australia Staff and Students, Shenton College Businesses and enterprises operating in the Western Australian primary industry sector | Major Risks Teachers and students may not be interested in participating |
| --- | --- |
|  | Related Projects Schools project: Science in Primary Industry (Grains Research Development Corporation) |

Governance

| Funding Body Australian Sheep CRC | Project Team Colin Hawke, Science in Primary Industry Project Officer, UWA Pauline Coughlan, Principal, Shenton College Mike Evans, Head of Middle School, Shenton College Trevor Whittle, Science Teacher, Shenton College Gabbi Barrett, English Teacher, Shenton College Patrick Durack, SOSE Teacher, Shenton College Gary Adamson, Art Teacher, Shenton College Katrina Boser, Community Liaison Officer, Agric. WA |
| --- | --- |
| Funding Body Australian Sheep CRC |  |
| Project Sponsor Dr. David Russell, Primary Industry Science (Education), UTAS |  |
| Host Organisation School of Agriculture, UTAS |  |
| Project Manager Warwick Mathews, Academic Talent Program Coordinator, Shenton College |  |

Consultants

Sheep industry leaders/ scientists as identified during the project description

Project Milestones

|  | Description | Who | Start | Finish |
| --- | --- | --- | --- | --- |
| 1 | Rough-out project plan | Mathews | February | April |
| 2 | Negotiate teacher release: Principal | Mathews | April | April |
| 3 | Identify and engage industry contact | Mathews | April | April |
| 4 | Identify and engage Agric. WA contact | Mathews | April | April |
| 5 | Identify and engage UWA contacts | Mathews | April | May |
| 6 | Book professional Learning venue | Hawke | April | May |
| 7 | Identify and invite teaching staff to attend PL | Mathews | May | May |
| 8 | Confirm presenters- breakfast; | Mathews | May 6 | May15 |
| 9 | Negotiate: media unit to film parts of event. Invite senior school (biology) to attend | Mathews | May6 | May15 |
| 10 | Newsletter: Notify whole school of event | Mathews | May 20 | May20 |
| 11 | Cross-curricula program development workshop | Mathews/ Hawke | May 26 | May26 |
| 12 | Collate and share program to relevant teachers, team leaders and Heads of school | Mathews | June 2 | June 4 |
| 13 | The Sheep at School day: coordinator | Mathews | June 15 | June15 |
| 14 | Gather survey forms and prepare report on project, include DVD, CD | Mathews | June 15 | June21 |
| 15 | Reporting and feedback session UTAS | Mathews | June |  |

Budget and Expenditure

| Month | Teachers’ PD | School Industry Links | Other | General | Total |
| --- | --- | --- | --- | --- | --- |
| March | Initial Contacts. Easter break, followed by two week term break. March- April | Initial contacts Easter break, followed by two week term break. March- April | Easter break, followed by two week term break. March- April | Easter break, followed by two week term break. March- April |  |
| April | Preparation of materials for teacher release and negotiating for scientist and industry personal $400 |  |  |  | $400 |
| May | Teacher Release to workshop: prepare special integrated rural curriculum 8x$300= $2400 Working breakfast: teachers, UWA, AgWEST and industry personal 12 x 25= $300 Venue hire for workshop $100 | Curriculum links English: literature, news articles Society and Environment: natural systems, economics Maths: Fleece weights, cost/ kg, production costs, percentages Science: genetics, breeding, nutrition Art: sheep sculpture, texture art, fabrics. |  |  | $2800 |
| April |  |  | 4x$300=$1200 Coordinator’s visits and organisation time | Resource development: distribution to teachers/ other states. Contract payments $2500. CD prep and burning $250 Printing and consumables $250 | $4200 |
| June | Event for two groups (60) of select students Teacher release to facilitate days 6x 300 =$1800 | Sheep farmer truck sheep in; supply sheep dogs; ultra sound pregnancy test; bioshearing, shearer $600 | In-kind UWA staff, Teacher preparation and coordination ($3000-4000) | Bus hire $300 Purchase 3x fleece and Art materials $250 Special lamb cuts for demo lunch/BBQ 75 x 8 =$600 | $3550 |
| June |  |  |  | Reporting and feedback session at UTAS. Airfare, accommodation’ Networking $1500 | $1500 |
| Total payment | $12450 |