Proposal for the Tasmanian Project

Title

Science and Wool

Objectives

- To increase the knowledge and understanding by science teachers and student career planners of the high level science underpinning the Australian wool industry.

- To increase the knowledge and understanding by teachers and career planners of the Working in Wool industry induction program.

- To pilot a program with high school students investigating the science behind wool production through a field trip and practical experiments.

Scope

Science & Wool is a one-and-half day professional development session for science teachers and pathway planners that showcase the science behind the Australian wool industry. This will include visits to laboratories, sessions with wool industry scientists on their current work and an evening networking function where teachers/planners will have the opportunity to meet with science professionals with careers in the wool industry.

Science & Wool will conclude on the last day of the Working in Wool program which is held at the Campbell Town show on 2 June. This will enable the teachers and pathway planners to meet the students who participated in this program and experience their enthusiasm for the broad range of careers available in agriculture, in particular in science.

The pilot program will be done with Sheffield High Students who will visit DPIWE in Launceston to see science in the wool industry in practice and then take back with them information to implement their own practical program.

Reason

The recently released Creating our Future Report1 (p. 106-106) highlights that Australian “farm and food business are becoming increasingly sophisticated, requiring a highly educated and skilled workforce.” This report also outlines that whilst there have traditionally been low levels of tertiary education amongst agricultural workers, this is starting to change with the agricultural sector demonstrating significant increases in education qualifications when compared to the average workforce. “The number of university graduates involved in agriculture has tripled in 20 years to 2004, however, recent years have shown a decline in interest in agriculture at higher education institutions.”  Lastly, this report states that “it is important that the proportion of workers in agriculture with post-school qualifications grows over time with …a long term decline in the number of university graduates in agriculture could affect the sector’s ability to change and adopt new practices.”

1 Agriculture and Food Policy Reference Group 2006, Creating Our Future: Agriculture and Food Policy for the Next Generation, Report to the Minister for Agriculture, Fisheries and Forestry, Canberra, February 2006.

Outputs

- Science & Wool, a professional development session with 10 science teachers/pathway planners highlighting the science behind Australian wool production.

- Science & Wool will be a model for similar sessions across other agricultural sectors.

- A pilot program for high school students demonstrating practical science behind wool production in Tasmania

- Successful delivery of the Science & Wool professional development session.

- Pre- and post-participation surveys of those undertaking Science & Wool to determine their understanding of the science and careers supporting Australia’s wool industry.

- Successful delivery of the high school student program.

Resources

- DPIWE, UTAS, Education and OPCET staff to develop program.

- Office space, computers, internet, printers, mobile phones and access to a government vehicle for period of project.

- Key wool/agricultural industry consultant a with science background to facilitate the program as an industry professional.

Budget & Expenditure

| Teachers’ PD Science & Wool | School Industry Links -Sheffield | Total |
| --- | --- | --- |
| Information gathering and preparation of information folders for participants 12 x $25 = $300 Promotional flyers etc $500 |  | $800 |
| Direct expenses of leading private sector scientists to participate (ie wool fibre testing, vet etc) =$1000 |  | $1,000 |
| Teacher release to participate in program (2 days) 10 x $600 = $6000 Bus Hire = $800 Meals & Accommodation 10 x $1800 = $1800 Industry networking dinner (20 people) $1500 | Pilot program with Sheffield High School Students Bus, teacher relief and materials = $600 | $10,300 |
| Total payment |  | $12,500 |

Government Agencies

- Department of Primary Industries, Water and Environment (DPIWE)

- Department of Education

- Office of Post-Compulsory Education and Training (OPCET)

- University of Tasmania (UTas)

- Tasmanian Institute of Agricultural Research (TIAR)

Peak Industry Bodies

- Tasmanian Farmers and Graziers Association (TFGA)

- Women in Agriculture (WiA)

- Tasmanian Institute Agricultural Research (TIAR)

- Businesses and enterprises operating in the Tasmanian primary industry sector

Major Risks

- Teachers and pathway planners are not interested in participating.

- Students not interested in participating.

Related Projects

Cropping a Career, Working in Wool, A Taste for Dairying, Year 10 School Scientific Research Awards are programs already being undertaken by Tasmania’s agricultural industry.

Governance

| Business Owner: Wes Ford, General Manager (Primary Industries), DPIWE | Project Team: Carolyn Claridge, Project Officer, DPIWE Caroline Brown, Program Officer, DPIWE Andrew Bailey, Agricultural Officer, DPIWE Alan Beach, VEL Development Officer, OPCET Christine Storey, VEL Development Officer, OPCET Tim Wilson, Science Education Officer, UTas Jacob Tammens, Advanced Skills Teacher, Sheffield District High School |
| --- | --- |
| Project Sponsor: Alan Johnston, Manager, Regional and Business Development, DPIWE |  |
| Project Manager: Tracey Taylor, Communications Specialist, DPIWE |  |

Consultant/s:

Wool industry leaders/scientists as identified during project

Project Milestones

| Id | Description | Who | Scheduled Start | Scheduled Finish |
| --- | --- | --- | --- | --- |
| 1 | Prepare and circulate draft project plan | Taylor | 24 February | 28 February |
| 2 | Meet with OPCET to discuss program and access to teachers/career planners | Taylor | 24 February | 3 March |
| 3 | Draft program for the event | Taylor, Bailey, Wilson, Beach | 6 March | 17 March |
| 4 | Publicise program to targeted teachers/career planners | Taylor Beach | 3 April | 14 April |
| 5 | Prepare and distribute applications and surveys etc | Taylor | 1 March | 30 April |
| 6 | Manage budget and payments | Claridge | 24 February | 30 June |
| 7 | Organise bus and accommodation | Claridge | 1 April | 30 June |
| 8 | Identify and contract industry professional scientist to facilitate the program | Taylor | 1 March | 1 May |
| 9 | Gather and prepare materials for participant folders Put together folders | Taylor, Claridge, Brown | 1 March | 30 May |
| 10 | Organise and host evening event – including venue, catering, guest list etc | Brown, Taylor, Claridge | 1 March | 2 June |
| 11 | Coordinate the days with the Working in Wool program | Taylor | 1 March | 2 June |
| 12 | Deliver the program to 10 teachers/career planners | Taylor, Claridge, Brown, Bailey | 1 June | 2 June |
| 13 | Gather completed survey forms and prepare report on project | Taylor, Claridge, Brown, Bailey | 2 June | 15 June |
| 14 | Develop and deliver pilot student program for Sheffield High School | Tammens, Bailey, Taylor | 1 March | 2 June |
| 15 | Reporting and feedback session at UTas | Taylor | June |  |